## Slide 1: Emilia-Romagna Region (PP6) Project Progress
Katia Raffaelli, Luisa Perini, Maria Romani
Adriatic Sea regional meeting
Kotor, 27th March 2007

## Slide 2: Current status
Pilot projects launched
National Report first draft
Internal meeting to present PlanCoast project: 9th October 2006
Regional meeting to present pilot projects to local authorities and stakeholders: 17th November 2006
External consultants engaged
Report “INTERREG Emilia-Romagna” (November 2006)
Dossier “La difesa della costa” (February 2007)

## Slide 3: WP2 Pilot Project Creation of a GIS Database as a basis for spatial planning
Update of Emilia-Romagna GIS coast database (SIC): a tool for spatial planning

## Slide 4: Pilot project objectives
Implementation of the Emilia-Emilia-Romagna Coast Information System (SIC), which was at first created to contain data concerning the physical coastal system (geology, geomorphology, land use, etc) and tools for coastal risk evaluation, with new topics specifically oriented to spatial planning process in coastal and maritime zones
Application of SIC contents to WP4 pilot project.

## Slide 5: Pilot project activities
Selection of the new topics which have to be joint to the SIC
Definition of the informative layers to develop for each topic
Examination of the existing information available into the Emilia-Romagna Regional archives and by all Regional or National Institution competent for coastal or maritime areas
Data collection, storing and processing
Elaboration of new themes at regional scale, as result of data analysis and overlapping
Arrangement of the cartography to be applied to the WP4 pilot project

## Slide 6: State of the Art
Collecting information from the different Institutions and implementing the topic concerning the “sea use”
Implementing a database about general town-planning schemes with a shared data model

## Slide 7: WP4 Pilot Project Realisation and evaluation of the ICZM Strategy
Implementation of the ICZM GuideLines into the local scale in order to valuate the impacts of planning strategies

## Slide 8: Pilot project objectives
Adopting ICZM guidelines in Territorial Coordination Plan (PTCP) of Ferrara Province
Deepening of nine thematic areas defined by ICZM guidelines at provincial scale
Characterisation of interactions between the PTCP and environmental system
Main aim: PTCP will be an integrated tool of different plans and policies regulating the coastal zones

## Slide 9: Pilot project activities
Definition of the territory borders for the application of ICZM guidelines
Interactions between the ICZM themes and the field of competence of the territorial planning
Elaboration of the cognitive picture, the whole range of information acquired during the analysis phase
Thematic maps for characterisation of interactions between the territorial plans and the environmental system and for characterisation of mitigation actions and their evaluation in term of sustainability
Elaboration of a preliminary document with specific objects for the reduction of probable critical point through VALSAT document
Elaboration of a Valsat document to define environmental, territorial/social, health and safety, and landscape qualification indicators of sustainability
Defining of monitoring indicators to evaluate PTCP’s effects.

## Slide 10
SPATIAL
PLANNING
The physical system
defence strategy
natural risks
Integrated water management
at basin scale
Port, transport,
navigation related risks
and management
Enlargements of natural habitats and improvement of biodiversity
Sustainable
tourism
Fishing and acquaculture
Sustainable
agricolture
Energy policy
Interaction between spatial planning and ICZM themes

## Slide 11: State of the Art
Writing the cognitive picture
Assessment of interactions between thematic areas
Thematic maps/paper development

## Slide 12: WP4 State of the Art All Pilot Projects

## Slide 13: WP4 Pilot Projects
(IT) Implementation ICZM principles in the spatial redevelopment of Palombina Beach
(PL) Projects of spatial plans for pilot coastal areas in West-Pommerian region
(SL) New municipal spatial plan for Piran
(AL) Study on the future land use and planning based on stakeholders participation
(BG) Updating of spatial plans for 7 coastal municipalities according to ICZM principles
(RO) Proposal of a new spatial plan for Constanta coastal area and Danube Delta

## Slide 14: WP4 State of the Art – Progress Report
Partner | 
Contact person | 
Date | 
Name of Pilot Project | 
Project objectives | 
Project activities | 
Project progress - State of the Art | 
Problems and issues | 
Further comments | 

## Slide 15: WP4 State of the Art – Romania
Name of Pilot Project | Pilot Project RO1 Sulina
Project progress State of the Art | Contacts have been initiated with the chief architect of Tulcea County which manifested interest and offered support for the actions under this Pilot Project. The Sulina General Urban Plan which is enacted is already 6 years old and need to be updated.
Name of Pilot Project | Pilot Project RO2 Southern Romanian Black Sea Coastal Area
Project progress State of the Art | PP13 INCDM is localized in Constanta, the main city from the Southern Coastal Area and already has contacts with different important actors from the area. Parts of the database are already established and some need just to be updated.

## Slide 16: WP4 State of the Art – Slovenia
Name of Pilot Project | Prepare a new municipal spatial plan for the municipality of Piran
Project progress State of the Art | The project was presented also to the other two coastal municipalities of Izola and Koper. Both of them shown an interest to cooperate in the WP4’s activities. The redefinition of the Terms of reference for including all the three slovenian coastal municipalities in the activities of WP4 is in progress now. An external expert was engaged for the preparation of spatial planning documentation. A draft of aspects of tourist development is prepared .

## Slide 17: National Report on current policy, procedures, practice of spatial planning in ICZM

## Slide 18: Some contents
There is no National Strategy
Some examples at regional scale: Emilia-Romagna, Liguria, Toscana, Marche
Complex set of spatial planning and environment protection laws
Developing ICZM strategy in compliance with Barcelona Convention in Mediterranean Action Plan

## Slide 19
Thanks for your attention