## Slide 1: PROGRESS REPORT (1)
1. SUMMARY of PAP/RAC activities
    National Reports - current policy, procedures, legal basis, practice of marine spatial planning (B spatial planning system, E marine spatial planning, 5 recommendations)
    Synthesis Report - spatial planning in the Adriatic + recommendations (integration of marine spatial planning in ICZM at national level. Link to Transnational study).
    Report on marine spatial planning - theoretical insight + experiences, + recommendations. (Link to Transnational study.)
    Conference on Marine Spatial Planning (3rd PlanCoast Meeting; Split, 20-21 September 2007)
  Contract with EC Delegation in Croatia signed 29 December 2006!
  10% reduction of the budget

## Slide 2: PROGRESS REPORT (2)
2. National Reports
Common ToR (Chapters co-financed by PAP/RAC)
  A Executive summary
  B General description of the spatial planning system in the country
  C Specificities of spatial planning in coastal zones
  D ICZM
  E Marine Spatial Planning
  F Linkages to International Policy
  G Annexes
  5 Recommendations
Co-ordination with partners and consultants (contracts, deadlines)
Comments/suggestions on draft/final reports (overall) Deadlines!!
Editing and publishing of complete National Reports

## Slide 3: PROGRESS REPORT (3)
3. Progress on National Reports

## Slide 4
UNEP Mediterranean Action Plan
Priority Actions Programme
Regional Activity Centre (PAP/RAC)
Kraj Sv. Ivana 11
21000 Split, Croatia
Tel: + (385) (21) 340 470
E-mail: pap@gradst.hr
www.pap-thecoastcentre.org