## Slide 1: by Susan Toben Ministry for Labour, Building and Regional Development M-V Germany Lead Partner
ICZM Strategy Development Process The PlanCoast Input from WP 1
Kick-off Meeting 13./14. July 2006

## Slide 3: What do we want to achieve?
Contribution of Spatial Planning to a
successful implementation of ICZM and
the EU Maritime Strategy
by
corresponding recommendations

## Slide 4: Central questions of the EU Green Paper of Maritime Policy concerning ICZM and Spatial Planning
How can ICZM be successfully implemented?
What are the principles and mechanisms that should underpin maritime spatial planning systems?
How can systems for planning on land and sea be made compatible?

## Slide 5: What can Spatial Planning offer to ICZM and the EU Maritime Strategy?
  Proven methods of participation and conflict management
  Binding results based on statutory plans
  Provision of space oriented data through Geographical Information Systems (GIS)

## Slide 6: Which steps will be necessary to elaborate our contribution?
Transnational comparative study
National reports on the current ICZM preconditions
Recommendations on Maritime Spatial Planning
Recommendations on Spatial Planning in ICZM
Results and Expe-rience of WP 2-4
Results and Expe-rience of WP 2-4
Regional study Adriatic Region

## Slide 7: Collection and assessment of current policy documents in each partner Country
Who‘ s responsible?: Each partner for his country by himself
When?: Start now until October 2006
What should be collected?: Common terms of reference (considering the guidance notes for completing the Progress Indicator of the EU WG on Indicators and Data)

## Slide 8: National reports on the current ICZM preconditions and regional Study for Adriatic Region
Who‘ s responsible?: Each partner for his country by himself
When?: October 2006 until March 2007
What should be reported?: Common terms of reference

## Slide 9: Transnational comparative study on the current role of spatial planning in ICZM and actual state of maritime spatial planning
Who‘ s responsible?: WP Leader in close collaboration with all partners
When?: March until September 2007
What should be compared?: Common terms of reference

## Slide 10: Evaluation of Pilot projects
Who‘ s responsible?: WP Leader in close collaboration with all partners
When?: September until December 2007
What should be compared?: Common terms of reference

## Slide 11: Recommendations on the implementation of national ICZM strategies and on the introduction of maritime Spatial Planning
Who‘ s responsible?: WP Leader in close collaboration with all partners
When?: October 2007 until February 2008
What should be recommended?: Based on transnational study and results and experience from WP 2- 4

## Slide 12: How to finance WP 1?
  Activities financed via specific partner budget:
  Data collection and assessment as well as national reports each partner for himself (own personnel or external experts)
  In some cases regional studies (e.g. Adriatic Region) also from specific partner budgets
  Any travel for working groups from own partner budgets

## Slide 13: How to finance WP 1?
  Activities financed via common budget:
  Transnational comparative study from common budget (external expertise) by all partners as foreseen in the project application
  Evaluation of pilot projects from common budget (external expertise) by all partners as foreseen in project application
  Recommendations from common budget (external expertise) by all partners as foreseen in the project application

## Slide 14: Thank you very much for your attention!

## Slide 15: Questions to discuss
  How we can ensure the added value of our work in the frame of WP 1?
  What material could be used?
  How does the timetable of WP 1 fit with other ICZM and maritime Spatial Planning relevant processes?
Notes:   Information of represents from Adriatic, Baltic and Black Sea Region as well of regional Organisations